## Sheet1
Bug Report
|  |  | Project Name | https://next.practiz.xyz
|  |  | Created By | Afifa Saeed
|  |  | Created Date | 2026-12-04
Bug ID | Title | Description | Steps to Reproduce | Expected Result | Actual Result | Severity | Bug Type | Environment | Status | Reported By | Screenshot Link
BUG-01 | Invalid email accepted during registration | System allows user to register using an invalid email format | 1. Go to Register page 2. Enter first & last name 3. Enter email 'afifa@abc.com' 4. Enter password 5. Click Register | System should show 'Invalid email' error | Account is created without validation | Medium | Functional | Chrome / Windows 10 | Open | Afifa | SS01
BUG-02 | Invalid email accepted for password recovery | System allows user to use an invalid email for password recovery | 1. Go to Login page 2. Click on 'Forget password?' 3. Enter email 'afifa@abc.com' 4. Send Reset Link | System should require a vlaid email | Email has been sent to invalid email | Medium | Functional | Chrome / Windows 10 | Open | Afifa | SS02
BUG-03 | Password Reset Page Displays Full Email | System exposed the full email without maintaing any privacy | 1. Go to Login page 2. Click on 'Forget password?' 3. Enter email 'afifa@abc.com' 4. Send Reset Link | Email should be displayed as : af***@abc.com | Full email exposed | Low | Security | Chrome / Windows 10 | Open | Afifa | SS03
BUG-04 | Assessments Page | Page takes too long to load the list of assessments, or spinner keeps running indefinitely. | 1. Login to the app 2. Go to Assessments 3. Select any program (e.g., ISEE Upper) 4. Observe loading time | Assessments list should load within 3-5 seconds and display all available assessments | Spinner keeps running for a long time; | Medium | Performance | Chrome / Windows 10 | Open | Afifa | SS04
BUG-05 | UI Header Overflow & Responsiveness | The top navbar is not responsive; utility icons and the user profile overflow off the screen, making them hard to access | 1. Login to the app 2. Click on the Assesments on the left 3. Right Click on the page and select Insspect from the drop down 4. Click on the Dimensions and select 'Samsung Galaxy S8+' from the drom down | Header elements should wrap, stack, or use a hamburger menu to fit the 360px width. All icons and the profile name should be fully visible and aligned. | Navigation icons and the user profile name 'Afifa' overflow horizontally, causing them to be cut off or unclickable. | Medium | Usability | Chrome / Windows 10 | Open | Afifa | SS05
BUG-06 | GraphQL API Error Leak on "Unfavorite" Action | Raw JSON GraphQL error displayed when removing an item from Favorites. | 1. Navigate to the Assessments page. S2. elect the Favorite tab. 3. Click the Heart icon (Unfavorite) on an existing assessment (e.g., "The Ultimate SAT/ACT Decision Test"). 4. Observe the notification popup on the right. | The item should be removed from the list, and a user-friendly message like "Removed from favorites" should appear. | A toast notification appears displaying a raw JSON error object ("message": "Favorite not found", "code": "NOT_FOUND"). This indicates the system is passing a null ID for the deleteFavorite operation | High | Functional | Chrome / Windows 10 | Open | Afifa | SS06
BUG-07 | Favorite Tab Discrepancy | Favorite tab shows a count of "1" but displays "No Assessments available" empty state | 1. Navigate to the Assessments page. 2.Click on the Favorite tab. | Since the tab badge indicates "1", one favorited assessment should be visible in the list below | The UI displays the "No Assessments available" empty state illustration and text, contradicting the badge count of 1 | Medium | Functional | Chrome / Windows 10 | Open | Afifa | SS07
BUG-08 | Unexplained "Sort by 1" Badge | "Sort by" button shows a badge count of "1" by default with no user action | 1. Navigate to the Classrooms page. 2. Observe the "Sort by" button on the right side of the search bar. | The badge should be hidden (or show '0') if no manual sorting is applied. If a default sort is active, the label should be descriptive (e.g., "Sort by Name") | The button shows "Sort by 1". This is confusing because the number "1" doesn't explain what is being sorted | Low | UX/UI | Chrome / Windows 10 | Open | Afifa | SS08
BUG-09 | Quiz Tab Badge Inconsistency | Quiz tab badge shows "0" while the list displays 9 available quizzes. | 1. Navigate to the Assessments page. 2. Select Program: SAT from the dropdown. 3. Observe the Quiz tab badge count. | The badge on the "Quiz" tab should display "9" to accurately reflect the number of quiz items visible in the table | The badge displays "0" | Medium | Functional | Chrome / Windows 10 | Open | Afifa | SS09
BUG-10 | Unexpected Page Refresh | Assessment page triggers an automatic reload after period of inactivity | 3. Navigate to the Assessments page. 2. Leave the tab open and idle for a significant period (e.g., 5-10 minutes). 3. Observe the browser behavior. | The page should remain static unless the user manually refreshes or a specific real-time update | The page reloaded by itself, potentially causing a loss of scroll position or unsaved search queries | Medium | Performance | Chrome / Windows 10 | Open | Afifa | SS10